## Slide 1
https://www.officetimeline.com/14-days-trial

## Slide 2
2017
2019
Today
December
Jul
Oct
2018
Apr
Jul
Oct
2019
Apr
Kick-Off
Minimal Prototype
9/30/17
Submission
11/25/17
Release Web Prototype
3/1/18
Online Testing
5/20/18
Release
3/15/19
Integration
10/30/17
Validation
7/22/18
Exec Review
1/1/19
System Design
143 days
5/17 - 11/17
80%
Coding
74 days
11/17 - 3/18
73%
Code Improvements
129 days
3/18 - 8/18
56%
Stabilization
42 days
8/18 - 10/18
20%
Integration with Website
77 days
8/18 - 11/18
15%
User Acceptance
99 days
10/18 - 2/19
Documentation
104 days
1/19 - 5/19